Project Plan

Crowd Density and Stampede Early-Warning System

AI-based computer vision monitoring for public safety

| Item | Detail |
| --- | --- |
| Based on | SRS v1.0 (Draft): Crowd Density and Stampede Early-Warning System |
| Project theme | Computer Vision: AI-based Monitoring, Scene Understanding, Behaviour Tracking |
| Team / event | [Enter team name] / [Enter college and hackathon name] |
| Plan version / date | 1.0 / [Enter date] |

# 1. Objective and approach

Deliver a working, offline, single-camera early-warning tool that converts live or recorded video into calibrated crowd density (people/m²), detects unsafe motion patterns, forecasts the time remaining before a zone becomes critical, and sends operators an alert with a recommended action. The tool is decision support only; it does not control gates and does not claim to prevent stampedes.

The build follows the SRS pipeline in order, so each phase produces something demonstrable and each phase closes against specific requirement IDs and acceptance tests.

# 2. Key technical decisions

| Decision | Choice | Rationale |
| --- | --- | --- |
| Density to people/m² | Ground-plane homography is primary; Depth Anything V2 Small is a secondary correction and confidence input | Four ground points give a real metric mapping. Monocular depth alone gives only approximate scale, as the SRS notes. Zone area comes from the warped polygon; zone count is the sum of the density map inside it. |
| Crowd counting | CLIP-EBC density map, run every N frames | Keeps throughput at or above 5 fps (NFR-02) while display and flow run faster. |
| Flow analysis | OpenCV Farneback optical flow per zone | Cheap, CPU-capable, covers FR-07 and FR-08. ByteTrack remains optional. |
| Choke-point counts | Line-crossing on flow vectors first; ByteTrack later if time allows | Meets FR-09 without an extra dependency. |
| Forecast | Exponential smoothing plus rolling linear slope, giving time to threshold | Simple, explainable, testable on simulated sequences. |
| Backend and UI | FastAPI with WebSocket streaming and a single-page dashboard with authentication | Fully offline; satisfies NFR-10. |
| Storage | SQLite for config, alert log, optional snapshots | Matches the SRS software interfaces. |
| Licensing | Depth Anything V2 Small only (Apache-2.0) | Base, Large and Giant are non-commercial. |

# 3. Phased delivery plan

Durations are expressed as a share of the total time available so the plan scales to the event length. Adjust the calendar once the hackathon duration is confirmed.

| Phase | Work | Share | Covers | Exit criterion |
| --- | --- | --- | --- | --- |
| 0. Setup | Repo, virtual environment, config system. Load CLIP-EBC and Depth V2 Small and run both on a sample clip. | 8% | FR-01, NFR-08, NFR-09 | Density map and depth map saved for one frame |
| 1. Capture and counting | Capture module (webcam, RTSP, file, reconnect). Counting module. Frame-skip scheduler. | 12% | FR-01, FR-02, NFR-06 | Live counts at 5+ fps |
| 2. Calibration and density | Four-point homography, zone area, people/m², heatmap with legend. | 17% | FR-03, FR-04, FR-05 | AT-01 passes |
| 3. Zones, flow, choke points | Polygon and line drawing, per-zone values, optical flow, opposing-flow and stop-and-go detection, inflow/outflow. | 17% | FR-06 to FR-09 | AT-02 passes |
| 4. Forecast and alerts | Time-to-critical, four-state rules with hysteresis, alert objects, Telegram or email, SQLite log, CSV export. | 17% | FR-10 to FR-14 | AT-03 and AT-04 pass |
| 5. Dashboard and evaluation | Live view, zone panel, alert feed, setup wizard, replay and metrics page, authentication, confidence indicator. | 17% | FR-15, FR-17, NFR-01 to NFR-04, NFR-10 | Full demo in replay mode |
| 6. Hardening and submission | Disconnect test, privacy audit, README, slides, demo script, dry runs. | 12% | NFR-05 to NFR-07, FR-16 | AT-05 and AT-06 pass; all six tests green |

# 4. Minimum viable product and cut line

## 4.1 Must ship

- Video ingest, CLIP-EBC density, four-point calibration, people/m² heatmap (FR-01 to FR-05).

- Zone and choke-point drawing (FR-06).

- Forecast, four-state classification and alert text (FR-10 to FR-12).

- Local-only processing and replay mode (FR-16, FR-17).

## 4.2 Cut first if time runs short

- ByteTrack integration.

- Confidence indicator (FR-15).

- WhatsApp and SMS delivery; keep one of Telegram or email.

- Advanced dashboard polish and multi-channel configuration screens.

# 5. Module and workstream map

| Module | Responsibility | Main requirements |
| --- | --- | --- |
| Capture | Read frames, resize, handle reconnects | FR-01, NFR-06 |
| Counting | Run CLIP-EBC; output density map and total count | FR-02 |
| Calibration | Homography, pixel-to-area scale, depth correction | FR-03, FR-04 |
| Flow | Motion vectors per zone; opposing flow and stop-and-go detection | FR-07, FR-08 |
| Choke points | Line crossings; inflow versus outflow | FR-09 |
| Forecast | Short-horizon trend and time to threshold | FR-10 |
| Alert engine | State rules, alerts, notifications, logging | FR-11 to FR-14 |
| Dashboard | Web UI, setup wizard, replay and metrics page | FR-05, FR-06, FR-15, FR-17 |

Suggested split for a small team: (A) vision core: counting, calibration, density; (B) motion and logic: flow, choke points, forecast, alert rules; (C) application: capture, API, dashboard, alert delivery, storage; (D) evaluation, documentation and demo. Agree interfaces between modules in Phase 0 so the streams can progress in parallel.

# 6. Alert logic (defaults)

| State | Default condition | Operator action |
| --- | --- | --- |
| Normal | Density below 2 people/m² and no turbulence | None |
| Watch | Density 2 to 3.5 people/m², or rising trend | Monitor zone |
| Warning | Density 3.5 to 5 people/m², or turbulence, or forecast under 10 minutes | Prepare to restrict entry; notify staff |
| Critical | Density at or above 5 people/m², or forecast under 3 minutes | Stop inflow, open alternate exits, dispatch staff |

The highest applicable state wins. Add hysteresis and a minimum dwell time to prevent flicker, and a per-zone alert cooldown to prevent spam. All thresholds live in configuration and must be reviewed by a qualified crowd-safety professional before any real deployment.

# 7. Evaluation plan

| Metric | Method | Output to report |
| --- | --- | --- |
| Counting MAE and RMSE | Run CLIP-EBC on a ShanghaiTech or UCF-QNRF test split | Value compared with the published baseline |
| Density error | Film a taped, measured floor area with a known number of people | Mean absolute error in people/m² |
| Lead time | Minutes between first alert and ground-truth critical event on test sequences | Average and range |
| False alarms | Alerts raised during normal sequences | Alerts per hour of video |
| Latency and FPS | Frame capture to dashboard update | Meets NFR-01 (2 s) and NFR-02 (5 fps) |

Any result derived from simulated crowd sequences must be labelled as simulated in the dashboard, the report and the slides. Never state a figure that was not measured.

# 8. Acceptance tests

| ID | Test | Pass condition | Phase |
| --- | --- | --- | --- |
| AT-01 | Load recorded video in replay mode and complete calibration | Heatmap displays in people/m² | 2 |
| AT-02 | Draw two zones and one choke point | Per-zone values appear on dashboard | 3 |
| AT-03 | Play a sequence with increasing density | State moves from Normal to Warning with forecast shown | 4 |
| AT-04 | Cause an alert to be raised | Appears on dashboard, sent externally, and logged | 4 |
| AT-05 | Disconnect the camera | System recovers within 30 seconds | 6 |
| AT-06 | Inspect stored data | No facial images or identities present | 6 |

# 9. Risks and mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Inaccurate scale from monocular depth | Wrong people/m² values | Homography as primary; report measured error; show confidence |
| False alarms | Operators lose trust | Multi-signal rules, hysteresis, tuned thresholds; report alerts per hour |
| Low frame rate on CPU | Misses NFR-02 | Configurable frame-skip, lower input resolution, GPU where available |
| Heavy occlusion, night, rain | Counting degrades | Confidence indicator; camera placement guidance in README |
| Scarce real stampede footage | Weak forecast validation | Validate on public data, recorded footage and labelled simulation |
| Privacy concerns | Public objection or misuse | No face recognition, local processing, minimal retention, visible privacy panel |
| Overstated claims | Loss of credibility | State clearly that this is decision support and what was validated |
| Model or data licence limits | Cannot commercialise | Use Depth V2 Small; check dataset terms |
| Live demo failure | Weak presentation | Rehearse in replay mode; keep a recorded fallback clip |

# 10. Demo script

- Load a recorded clip and calibrate in under 10 minutes using the setup wizard.

- Draw two zones and one choke point.

- Play a crowd build-up and show a zone move from Normal through Watch to Warning, with the time-to-critical countdown.

- Show the Telegram or email alert arriving with its recommended action.

- Open the alert log and export the CSV.

- Open the privacy panel: no faces, no stored video by default.

- Close on the replay page with MAE, density error, lead time and false alarms per hour.

# 11. Pre-start checklist

- Fill in the placeholders: team name, members, event, date.

- Confirm hackathon duration, then convert the phase shares above into dates.

- Obtain CLIP-EBC weights and a ShanghaiTech or UCF-QNRF test split.

- Record at least one clip of a taped, measured floor area with a known number of people.

- Create a Telegram bot token or email credentials; store them outside source code.

- Confirm target hardware (laptop or Jetson, GPU availability).

- Assign owners to the four workstreams and agree module interfaces.

Disclaimer: This system is a decision-support aid. It does not replace trained crowd-management staff, and threshold values must be reviewed by a qualified safety professional before real-world use.